## Lead
Project Name - E Medicare System
Group Number - 1
Team Lead & Frontend Lead- Akshay X & Amit Kumar
Backend Lead - Amitkumar Rajanal

## Status Track
Project Status Check Report Team - 1
Sl no. | Employee ID | Name | Domain | Module | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27
1 | 2485288 | A Sasank Reddy | Back-end & Front-end | Admin, Search, Medicine | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Admin & Search Components | Demo
2 | 2485265 | Aarthi Ellappan | Back-end & Front-end | Login,search | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Login Components | Demo
3 | 2485182 | Abburi Aruna | Back-end & Front-end | User, User | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | User Components | Demo
4 | 2484054 | Abhilash M | Back-end & Front-end | Cart, Cart | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Cart Components | Demo
5 | 2485376 | Aditya Kumar | Back-end & Front-end | Contact us, Contact | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Contact us Components | Demo
6 | 2484886 | Akkamahadevi X | Back-end & Front-end | Login,search | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Login Components | Demo
7 | 2484784 | Akshay Madhukar Kawade | Back-end & Front-end | Logout, Forgot password | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Logout Components | Demo
8 | 2485019 | Akshay X | Back-end & Front-end | User, Forgot password, User | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | User & Forgot password Components | Demo
9 | 2484661 | Amit Kumar | Back-end & Front-end | Admin, Search, Medicine | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Admin & Search Components | Demo
10 | 2487908 | Amitkumar Rajanal | Back-end & Front-end | Cart, Search, Cart | Group and Project Discussion | Model,Repository | Service, Controller | Exception,Integration | Cart & Search Components | Demo

## Status Meeting
Status Meeting Group - E Medicare System
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-03-22 | -- | -- | 2:30 | -- | 6:20 | --
2022-03-23 | 9:30 | a | 1:00 | a | 6:20 | a
2022-03-24 | 9:30 | a | 2:00 | a | 6:10 | a
2022-03-25 | 9:30 | a | 3:00 | a | 6:30 | a
2022-03-26 | 9:30 | a | 1:30 | a | 6:30 | a
2022-02-27 | 9:30 | a | 1:30 | a | 6:30 | a